## Cover
MediFind — Test Requirements Workbook
Emergency Response Ecosystem · Patient · Caregiver · Responder · Admin
Project: MediFind FYP ¦ Date: 2026-09-17 ¦ Version: 2.2 (results recorded; privacy, chat lock and calls added; v1.0 dated 2026-05-30)
STATUS LEGEND
PASS | Test passed — behaviour matches expected result
FAIL | Test failed — defect raised
PENDING | Not yet executed
N/A | Not applicable for this configuration
BLOCKED | Cannot be tested — dependency unresolved
HOW TO USE
1. | Edit only the Status (dropdown) and Notes / Defect Ref columns in each test sheet.
2. | SRS Ref links every test to a functional requirement in MediFind_Requirements_Analysis.docx; "Beyond SRS" marks extra features.
3. | SUMMARY and SRS_TRACEABILITY recalculate automatically from the Status and SRS Ref columns.
4. | CHANGE_LOG lists what changed from version 1.0 and why.
SHEETS IN THIS WORKBOOK
AUTH | Registration, Login, Lockout, Password Reset, Token Refresh, Logout
PATIENT_SOS | Hold-to-SOS, 60-second Countdown, Categories, Tracking, ETA, Cancellation
SECURITY_SOS | False SOS Prevention, Abuse Limits, Security Controls
RESPONDER | Alerts, Accept/Reject, Availability, Navigation, Status, Resolve
CAREGIVER | Linking, Live Map, Notifications, History
MEDICAL | Medical Profile, Reports, Emergency Contacts, Data Isolation
CHAT | Real-time Chat, Privacy, History, Quick Phrases (Deaf), Media
PRIVACY_CALLS | Contact Privacy, Emergency Chat Lock, Phone Calls, In-app Voice/Video Calls, Performance, AI & Layout
PROFILE | View/Edit Profile, Avatar Upload, Account Deletion (beyond SRS)
ACCESSIBILITY | Deaf Mode, High Contrast, Font Scaling, Voice Guidance, Vibration
NOTIFICATIONS | Self-hosted Push, In-App, Broadcast, Admin Web Portal
NAVIGATION_UI | Sidebar, Stateful Routing, Quick Actions, Performance
ADMIN_PORTAL | User Management, Verification, Dashboard, SOS Logistics
BACKEND_API | REST Endpoints, Auth Middleware, Sockets, Error Handling
SUMMARY | Pass / Fail / Pending counts per area (formulas)
SRS_TRACEABILITY | Every SRS functional requirement mapped to its test cases
CHANGE_LOG | Changes from version 1.0

## SUMMARY
MediFind — Test Requirements Summary
# | Test Area | Total | PASS | FAIL | PENDING | BLOCKED | N/A | Pass Rate
1 | AUTH
2 | PATIENT_SOS
3 | SECURITY_SOS
4 | RESPONDER
5 | CAREGIVER
6 | MEDICAL
7 | CHAT
8 | PRIVACY_CALLS
9 | PROFILE
10 | ACCESSIBILITY
11 | NOTIFICATIONS
12 | NAVIGATION_UI
13 | ADMIN_PORTAL
14 | BACKEND_API
TOTAL
Totals count test rows (section headers excluded). Pass Rate = PASS ÷ (Total − N/A).

## SRS_TRACEABILITY
MediFind — SRS Functional Requirement Traceability
FR ID | Module | Requirement (SRS) | Test Cases | Coverage | Test Case IDs
FR1.1 | Authentication | Register via email, full name, phone number, and role selection |  |  | AUTH-01, AUTH-02, AUTH-03, AUTH-04, AUTH-05, AUTH-06, API-01
FR1.2 | Authentication | Secure login with email/password + JWT (24h access / 30d refresh) |  |  | AUTH-07, AUTH-08, AUTH-09, AUTH-10, AUTH-11, AUTH-13, API-02, API-03
FR1.3 | Authentication | Three mobile roles: Patient, Caregiver, Emergency Responder |  |  | AUTH-01, AUTH-04
FR1.4 | Authentication | Administrator role via secure web dashboard |  |  | AUTH-16
FR1.5 | Authentication | Password reset via email verification + OTP |  |  | AUTH-14, AUTH-15
FR1.6 | Authentication | Role-Based Access Control (RBAC) |  |  | AUTH-07, AUTH-16, SEC-10, SEC-11, CG-04, API-10, API-11
FR2.1 | Medical Profile | Patients create and maintain a digital medical profile |  |  | MED-01, MED-02, MED-03
FR2.2 | Medical Profile | Profile: Blood Type, Allergies, Chronic Diseases, Medications, Disability Type (DEAF/NORMAL) |  |  | MED-01, MED-04
FR2.3 | Medical Profile | Medical Report Upload — camera or gallery (image/PDF) |  |  | MED-05, MED-06, API-12
FR2.4 | Medical Profile | View, rename, and delete reports |  |  | MED-07
FR2.5 | Medical Profile | Medical summary auto-transmitted to responder during active SOS |  |  | RSP-02, MED-08
FR2.6 | Medical Profile | HIPAA-compliant data isolation — reports only visible to patient + active responder |  |  | MED-09, API-15
FR3.1 | Accessibility | Specialized UI modes based on disability type (visual accessibility for deaf users) |  |  | AUTH-02, SOS-02, SOS-07, SOS-08, CG-03, CHT-03, CHT-06, PHN-04, CALL-03, CALL-11, ACC-01, ACC-02, ACC-04, ACC-12
FR3.2 | Accessibility | High-contrast themes + dynamic font scaling (up to 150%) |  |  | ACC-08, ACC-09, ACC-14
FR3.3 | Accessibility | Haptic feedback for SOS countdowns and incoming messages |  |  | SOS-02, CG-06, CHT-10
FR3.4 | Accessibility | Speech-impaired users operate without voice input — silent SOS + text communication |  |  | SOS-02, CHT-03, CHT-04, CHT-05, CHT-07, ACC-03, ACC-13
FR3.5 | Accessibility | Large-scale buttons for motor impairment assistance |  |  | ACC-10, NAV-05
FR4.1 | SOS Emergency | One-tap / long-press SOS button on home screen |  |  | SOS-01, SOS-12, SEC-01
FR4.2 | SOS Emergency | Auto-capture and transmit high-accuracy GPS coordinates on SOS activation |  |  | SOS-04, SEC-03, SEC-05
FR4.3 | SOS Emergency | Cancellation window with countdown timer (SRS: 10 s; implemented as 60 s by project decision) |  |  | SOS-01, SOS-03, SOS-14, SEC-02
FR4.4 | SOS Emergency | Emergency categorization: Cardiac, Respiratory, Fall, Trauma, etc. |  |  | SOS-10
FR4.5 | SOS Emergency | Notify all nearby available responders immediately |  |  | SOS-13, SEC-04, RSP-01, RSP-02, RSP-03, RSP-07, API-05
FR4.6 | SOS Emergency | Notify all connected caregivers instantly |  |  | SOS-09, CG-05, CG-09
FR5.1 | Responder & Voice | First responder to accept is atomically assigned — request closed for others |  |  | SEC-13, RSP-04, RSP-11, PRV-07, API-06
FR5.2 | Responder & Voice | Hands-free Voice Alert via TTS reads patient details to responder |  |  | RSP-05, RSP-06, ACC-05
FR5.3 | Responder & Voice | Voice alert includes emergency type, location, medical info, and DEAF status flag |  |  | RSP-05, PRV-03, PRV-04
FR5.4 | Responder & Voice | Responders toggle availability (Online/Offline) |  |  | RSP-12
FR6.1 | Live Tracking | Real-time responder location tracking via WebSockets |  |  | SOS-05, RSP-08, RSP-14, ADM-11, API-16
FR6.2 | Live Tracking | Responder route + ETA displayed to Patient and Caregiver |  |  | SOS-06, SOS-11, SEC-06, RSP-08, RSP-09, RSP-10, CG-08, PERF-03, API-07
FR6.3 | Live Tracking | Caregiver interactive map to monitor patient safety and location |  |  | CG-01, CG-08, API-13
FR6.4 | Live Tracking | Navigation hooks for responders to reach patient exact location |  |  | RSP-13
FR7.1 | Chat | Secure real-time chat between Patients and Caregivers via Socket.io |  |  | CHT-01, CHT-02
FR7.2 | Chat | Many-to-many: one patient to many caregivers; one caregiver to many patients |  |  | CG-01, CG-07, CHT-08
FR7.3 | Chat | Private chat silos — messages in one room never visible to others |  |  | CHT-09, PRV-01, PRV-02, LCK-01
FR7.4 | Chat | Instant message notifications with haptic alerts |  |  | CHT-10, NTF-06
FR7.5 | Chat | Persistent chat history for continuity of care |  |  | CHT-11
FR8.1 | UI & Navigation | Unified Sidebar (AppDrawer) navigation |  |  | NAV-01
FR8.2 | UI & Navigation | StatefulShellRoute — preserves navigation history, no UI flickering |  |  | CG-02, NAV-02
FR8.3 | UI & Navigation | Role-specific Quick Action Grids on dashboards |  |  | NAV-03
FR8.4 | UI & Navigation | 60FPS performance with optimized rendering techniques |  |  | PERF-01, PERF-02, NAV-04
FR9.1 | Admin | Secure Web-based Admin Dashboard |  |  | ADM-08
FR9.2 | Admin | List, filter, and search all users across all roles |  |  | ADM-01, ADM-02, ADM-09
FR9.3 | Admin | Deactivate or delete user accounts |  |  | AUTH-17, ADM-03, ADM-10
FR9.4 | Admin | Responder Verification Workflow — review pending applications |  |  | AUTH-03, RSP-03, ADM-06
FR9.5 | Admin | Approve (VERIFIED) or Reject responders with reason |  |  | ADM-04, ADM-05
FR9.6 | Admin | Real-time stats: total users, total emergencies, active emergencies, verified responders |  |  | ADM-07
FR9.7 | Admin | Only ADMIN role can access administrative endpoints |  |  | ADM-08, API-11
Requirements
Covered (2+ tests)
Minimal (1 test)
Gaps (0 tests)
Source: MediFind_Requirements_Analysis.docx (SRD modules 1–9). The document header says 39 FRs; the module tables list 47, all included here.

## AUTH
MediFind — AUTH Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
REGISTRATION
AUTH-01 | FR1.1, FR1.3 | Registration | Patient can register with name, email, password, phone, CNIC number and patient type (Normal/Deaf) | 1. Open app → Get started 2. Choose Patient → "I can hear" 3. Fill name, email, phone, CNIC, password (8+) 4. Submit | HTTP 201; OTP verification screen shown; 6-digit code emailed (valid 15 min) | Critical | PENDING
AUTH-02 | FR1.1, FR3.1 | Registration | Deaf patient can register with patientType = DEAF | 1. Register with patientType = DEAF 2. Complete all steps | Account created; deaf-specific onboarding tips shown; textOnlyMode defaults to true | Critical | PENDING
AUTH-03 | FR1.1, FR9.4 | Registration | Responder can register with CNIC (front/back), employee card, driving licence and motorbike documents | 1. Choose Responder 2. Fill organisation, licence no., motorbike no. 3. Upload all documents 4. Submit | Account created with verification PENDING; "Awaiting admin approval" screen; application appears in admin Verification Queue | Critical | PENDING
AUTH-04 | FR1.1, FR1.3 | Registration | Caregiver can register; linking to a patient happens after login by email invitation | 1. Choose Caregiver 2. Complete registration and email OTP 3. Log in → Link patient → enter patient email | Caregiver account created; invitation sent to patient (in-app + push + email); link shows PENDING until patient accepts | High | PENDING
AUTH-05 | FR1.1 | Registration | Duplicate email registration is rejected | 1. Register with an email already in the system 2. Submit | Error "User already exists with this email" shown; no duplicate account created | High | PENDING
AUTH-06 | FR1.1 | Registration | Password must meet minimum requirements (≥8 chars) | 1. Enter password with 5 characters 2. Submit | Validation error shown inline; form not submitted | Medium | PENDING
LOGIN
AUTH-07 | FR1.2, FR1.6 | Login | Registered user can log in with email and password | 1. Enter valid credentials 2. Tap Login | JWT token stored; user navigated to role-appropriate home screen | Critical | PENDING
AUTH-08 | FR1.2 | Login | Invalid credentials show an error and do not log in | 1. Enter wrong password 2. Tap Login | Error "Invalid credentials" shown; user stays on login; warning appears when 2 or fewer attempts remain | Critical | PENDING
AUTH-09 | FR1.2 | Login | Unverified account is blocked from logging in | 1. Register new account but do not verify email 2. Try to log in | Login denied with "Please verify your email before logging in"; OTP screen offered | High | PENDING
SESSION & LOGOUT
AUTH-10 | FR1.2 | Session | JWT token is refreshed before expiry | 1. Log in 2. Wait 29 minutes (near 30-min access token expiry) 3. Perform any API action | Token refreshed silently; user remains logged in without interruption | High | PENDING
AUTH-11 | FR1.2 | Logout | User can log out; session is fully cleared | 1. Log in 2. Navigate to Settings 3. Tap Logout | Tokens cleared from storage; user redirected to Login screen; back button does not return to protected screen | High | PENDING
AUTH-12 | Beyond SRS | Logout | After account deletion, user is redirected to Login screen without black screen flash | 1. Log in as any role 2. Go to Profile Settings 3. Tap Delete Account 4. Confirm in dialog | Account deleted; user redirected smoothly to Login screen; NO black screen / dark overlay flash during transition | Critical | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
AUTH-13 | FR1.2 | Login | Account locks for 30 minutes after 5 failed login attempts | 1. Enter wrong password 5 times 2. Enter correct password | Locked message with minutes remaining; correct password rejected until lock expires | High | PENDING
AUTH-14 | FR1.5 | Password Reset | User resets a forgotten password with an emailed 6-digit OTP | 1. Login → Forgot password → enter email 2. Enter OTP from email 3. Set new password (8+) | Password changed; old sessions signed out; login works with new password only | Critical | PENDING
AUTH-15 | FR1.5 | Password Reset | Reset/verification code is invalidated after 5 wrong attempts | 1. Request reset code 2. Enter a wrong code 5 times 3. Enter the correct code | After 5 wrong attempts: "Too many incorrect attempts"; the old code no longer works; a new code must be requested | High | PENDING
AUTH-16 | FR1.4, FR1.6 | Registration | Public registration cannot create an ADMIN account | POST /api/auth/register with role = ADMIN | HTTP 400 "Invalid role"; no account created | Critical | PENDING
AUTH-17 | FR9.3 | Login | Deactivated account cannot log in and existing sessions stop working | 1. Admin deactivates a logged-in user 2. User performs any action 3. User tries to log in again | API returns 401 "account has been deactivated"; app signs out; login denied | High | PENDING

## PATIENT_SOS
MediFind — PATIENT_SOS Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
SOS TRIGGER
SOS-01 | FR4.1, FR4.3 | SOS Trigger | Patient triggers SOS by holding the SOS button, choosing an emergency type, then a 60-second countdown before the alert is sent | 1. Press and hold SOS for ~2 s (progress ring fills) 2. Select emergency type 3. Watch the 60-second countdown reach 0 (or tap Send SOS now) | No request is sent during the countdown; at 0 the SOS is created (HTTP 201), patient enters searching/tracking screen, nearby responders notified | Critical | PENDING
SOS-02 | FR3.1, FR3.3, FR3.4 | SOS Trigger | Deaf patient can trigger SOS — no voice prompt plays during countdown or after submission | 1. Log in as Deaf Patient 2. Trigger SOS 3. Confirm 4. Monitor for any audio output | SOS triggered; NO TTS voice plays; vibration feedback fires if enabled; full-screen visual confirmation shown | Critical | PENDING
SOS-03 | FR4.3 | SOS Trigger | SOS can be cancelled during the 60-second countdown without contacting the server | 1. Start SOS (hold + type) 2. Tap Cancel before the countdown ends 3. Check admin SOS Logistics | Countdown stops; user returns to Home; NO emergency record exists and no responder/caregiver is notified | High | PENDING
SOS-04 | FR4.2 | SOS Trigger | GPS/location permission is required; the app never sends a fake or default location | 1. Disable location permission or GPS 2. Try to send SOS | Prompt to enable location with "Open settings", "Try again" and "Call 1122"; SOS is not sent without a real fix | High | PENDING
EMERGENCY TRACKING
SOS-05 | FR6.1 | Tracking | Patient sees live responder location on map after responder accepts | 1. Trigger SOS 2. Accept from a logged-in Responder account 3. Observe patient tracking screen | Responder pin appears on map; pin updates every few seconds as responder moves | Critical | PENDING
SOS-06 | FR6.2 | Tracking | Status updates (ASSIGNED → EN_ROUTE → ARRIVED) shown on tracking screen | Trigger SOS → responder accepts → marks En route → Arrived → Resolves | Tracking screen timeline updates in real time: Assigned → En route → Arrived → Resolved | Critical | PENDING
SOS-07 | FR3.1 | Tracking | Normal patient receives voice status updates (TTS) when voiceGuidance is ON | 1. Enable Voice Guidance in Accessibility Settings 2. Trigger SOS 3. Responder changes status | TTS speaks "A responder has been assigned and is on the way" and subsequent status messages | High | PENDING
SOS-08 | FR3.1 | Tracking | Deaf patient does NOT receive TTS status updates regardless of settings | 1. Log in as Deaf Patient 2. Trigger SOS 3. Responder changes status 4. Monitor for audio | No TTS plays; visual status banner updates; vibration fires if enabled | High | PENDING
SOS-09 | FR4.6 | Tracking | Caregiver receives notification when their linked patient triggers SOS | 1. Log in as Caregiver linked to a patient 2. Trigger SOS from patient account 3. Check Caregiver device | Push notification and in-app alert received by caregiver | High | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
SOS-10 | FR4.4 | SOS Trigger | Patient selects a medical emergency category | 1. Start SOS 2. Review type options | Options: Cardiac, Stroke, Breathing, Trauma, Fall, Seizure, Diabetic, Other (medical only); chosen type shown to responder | High | PENDING
SOS-11 | FR6.2 | Tracking | Patient sees responder ETA that updates while the responder moves | 1. Responder accepts and drives toward patient | ETA (minutes) visible on tracking screen and decreases as responder approaches | High | PENDING
SOS-12 | FR4.1 | SOS Trigger | A quick accidental tap on SOS does not start an emergency | 1. Tap SOS briefly (< 1 s) | No countdown starts; hint "Press and hold to send SOS" shown | Critical | PENDING
SOS-13 | FR4.5 | SOS Trigger | A second SOS while one is open returns the existing emergency (no duplicate dispatch) | 1. Send SOS 2. Send SOS again before it closes | HTTP 200 with alreadyActive = true and the same emergency id; responders are not notified twice | High | PASS | 2026-09-17: second SOS returned the same emergency id (alreadyActive), no second dispatch
SOS-14 | FR4.3 | Cancellation | After sending, the patient can still cancel within the server cancellation window | 1. Let countdown finish (SOS sent) 2. Tap Cancel on searching screen before a responder accepts | Emergency CANCELLED; notified responders see the alert removed; not counted as a false alarm | High | PENDING
SOS-15 | Beyond SRS | Offline | Offline patient can still call or SMS Rescue 1122 | 1. Turn off internet 2. Open SOS | Non-blocking offline banner with working Call 1122 and SMS 1122 buttons | High | PENDING
SOS-16 | Beyond SRS | Rating | Patient rates the responder after resolution (once) | 1. Emergency resolved 2. Give 5 stars 3. Try to rate again | Rating saved and responder average updated; second rating rejected | Medium | PENDING

## SECURITY_SOS
MediFind — SECURITY_SOS Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
FALSE SOS PREVENTION
SEC-01 | FR4.1 | Trigger | SOS requires press-and-hold before it starts | 1. Tap SOS 2. Hold SOS for 2 s | Tap: nothing sent, hint shown. Hold: countdown starts with progress ring and vibration | Critical | PENDING
SEC-02 | FR4.3 | Countdown | Cancelling during the 60-second countdown sends nothing to the server | Start SOS and cancel at 30 s | No emergency record, no notifications | Critical | PASS | 2026-09-17: cancelling in the countdown created 0 emergency rows and 0 notifications (API/DB check)
SEC-03 | FR4.2 | Location | SOS from a mock (fake) GPS location is refused in production | Enable a mock location app and send SOS (production build) | HTTP 422 "fake (mock) GPS location" with Call 1122 advice; no dispatch | Critical | PENDING
SEC-04 | FR4.5 | Rate limit | More than 5 SOS in one hour is refused | Send and cancel SOS 5 times, then send a 6th | 6th request: HTTP 429 "Too many SOS requests" with Call 1122 advice | High | PASS | 2026-09-17: 6th SOS within an hour returned HTTP 429 with Call 1122 advice
SEC-05 | FR4.2 | Location | SOS outside Pakistan coordinates is refused | POST /api/emergencies with Dubai coordinates | HTTP 400 with coordinate error | Medium | PASS | 2026-09-17: SOS with coordinates outside Pakistan returned HTTP 400
FALSE ALARM HANDLING
SEC-06 | FR6.2 | Resolve | Responder must add a note when closing as False alarm or Patient not found | Resolve with outcome FALSE_ALARM and empty note | HTTP 400 "Please add a short note"; with a note the emergency closes with outcome saved | High | PENDING
SEC-07 | Beyond SRS | Warning | Patient is warned when an SOS is marked as a false alarm | Responder resolves as FALSE_ALARM | Patient receives "SOS marked as false alarm" notification | High | PENDING
SEC-08 | Beyond SRS | Review | 3 false alarms in 30 days alerts admins for review | Mark 3 SOS from the same patient as FALSE_ALARM | Admins receive "Patient flagged for repeated false SOS"; admin user profile shows the count | High | PENDING
SEC-09 | Beyond SRS | Fairness | Patient-cancelled SOS never counts as a false alarm | Cancel 3 SOS within the window | False alarm count stays 0; no admin alert | Medium | PENDING
PLATFORM SECURITY
SEC-10 | FR1.6 | Tokens | Refresh token cannot be used as an access token | Call a protected API with the refresh token as Bearer | HTTP 401 | Critical | PENDING
SEC-11 | FR1.6 | Sockets | Users cannot join emergency or chat rooms they do not belong to | Emit join:emergency / join:chat for another user's ids | Join refused; no events received | Critical | PENDING
SEC-12 | Beyond SRS | Payments | Paid plan upgrade requires a verified Stripe payment | PATCH /api/users/upgrade {plan: EXECUTIVE} without paymentIntentId | HTTP 402; plan unchanged | High | PENDING
SEC-13 | FR5.1 | Emergency | Only the assigned responder can update or resolve an emergency | Another responder calls status/resolve | HTTP 403 / 400; emergency unchanged | Critical | PENDING

## RESPONDER
MediFind — RESPONDER Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
INCOMING EMERGENCY ALERTS
RSP-01 | FR4.5 | Alert Receipt | Verified, available responder within 10 km receives the SOS alert in real time | 1. Responder online (availability ON) 2. Patient within 10 km sends SOS | Alert card on Responder home and a push notification (even when the app is closed) within ~2 s | Critical | PENDING
RSP-02 | FR2.5, FR4.5 | Alert Receipt | Alert shows patient name, emergency type, distance, ETA, DEAF badge and key medical flags | 1. Receive emergency alert 2. Inspect alert card | Card shows name, type, distance (km), ETA, DEAF badge if applicable, blood group/allergy badges | High | PENDING
RSP-03 | FR4.5, FR9.4 | Alert Receipt | Unverified responder does NOT receive emergency alerts | 1. Log in as PENDING/unverified Responder 2. Trigger SOS from patient | No alert received; unverified responder not included in dispatch | High | PENDING
ACCEPT / REJECT
RSP-04 | FR5.1 | Accept | Responder can accept emergency; patient tracking screen reflects ASSIGNED status | 1. Receive alert 2. Tap Accept 3. Check patient tracking screen | Status changes to ASSIGNED on patient screen; responder enters Active Emergency screen | Critical | PENDING
RSP-05 | FR5.2, FR5.3 | Accept | On accept, Voice Alert auto-plays patient details if voiceGuidanceEnabled is ON | 1. Enable Hands-Free Voice Alerts in Accessibility Settings 2. Accept emergency | TTS reads emergency type, location, allergies, blood group and the DEAF flag ("patient is deaf — communicate by text") | High | PENDING
RSP-06 | FR5.2 | Accept | On accept, NO auto-play voice if voiceGuidanceEnabled is OFF | 1. Disable Hands-Free Voice Alerts 2. Accept emergency | No TTS plays automatically; manual "Play Voice Alert" button still works | High | PENDING
RSP-07 | FR4.5 | Reject | Responder can reject; the SOS remains available to other notified responders and is re-dispatched if nobody accepts | 1. Two responders receive the same SOS 2. Responder A rejects 3. Wait 60 s without any accept | Alert removed only for A; B can still accept; after 60 s without accept the SOS is re-dispatched and admin receives an escalation alert | Medium | PENDING
STATUS UPDATES
RSP-08 | FR6.1, FR6.2 | Status | Responder can mark EN_ROUTE; patient sees update | 1. Accept emergency 2. Tap "On the Way" 3. Check patient screen | Patient tracking screen shows EN_ROUTE status | Critical | PENDING
RSP-09 | FR6.2 | Status | Responder marks ARRIVED; patient and caregivers are notified; the emergency stays open until the responder resolves it | 1. Accept SOS 2. Mark En route → Arrived | Patient sees "Help has arrived"; caregivers get an update (not a new SOS alert); status ARRIVED until Resolve | Critical | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
RSP-10 | FR6.2 | Status | Responder resolves the emergency with an outcome | 1. After arrival tap Resolve 2. Choose Treated on site | Emergency RESOLVED with outcome saved; responder becomes available; patient asked to rate | Critical | PENDING
RSP-11 | FR5.1 | Accept | Only one of two simultaneous accepts succeeds | 1. Two responders tap Accept at the same moment | One responder enters Active Emergency; the other sees "already assigned" and the alert disappears | Critical | PENDING
RSP-12 | FR5.4 | Availability | Offline responders are not dispatched | 1. Toggle availability OFF 2. Patient nearby sends SOS 3. Toggle ON and repeat | No alert while OFF; alert received after switching ON; toggle state persists after reopening the app | High | PENDING
RSP-13 | FR6.4 | Navigation | Navigate opens turn-by-turn directions to the patient | 1. Active emergency → tap Navigate | Google Maps opens with driving directions to the patient coordinates | High | PENDING
RSP-14 | FR6.1 | Tracking | Responder location is shared live every few seconds during an active emergency | 1. Accept SOS 2. Move for 1 minute | Patient, caregiver and admin live map show the motorbike ambulance moving smoothly | Critical | PENDING
RSP-15 | Beyond SRS | Assignment | Responder cancelling an accepted job re-dispatches the SOS | 1. Accept SOS 2. Cancel response (confirm) | Patient sees "Finding another responder"; other nearby responders receive the alert | Medium | PENDING

## CAREGIVER
MediFind — CAREGIVER Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
LINKED PATIENTS
CG-01 | FR6.3, FR7.2 | Linked Patients | Caregiver can view list of all linked patients on home screen | 1. Log in as Caregiver 2. Navigate to Home | List of linked patients shown with name, status, and last active time | High | PENDING
CG-02 | FR8.2 | Patient Profile | Caregiver can open a linked patient's profile with visible header and back navigation | 1. Log in as Caregiver 2. Tap a linked patient's card 3. Inspect the screen | Profile opens with "Patient Profile" AppBar title visible; back arrow present; bottom nav NOT shown | High | PENDING
CG-03 | FR3.1 | Patient Profile | Deaf patient badge shown on patient profile with caregiver-relevant subtitle | 1. View profile of a Deaf linked patient | Deaf badge shows subtitle: "Communicate via text chat • Cannot receive voice calls • Uses visual alerts" | Medium | PENDING
CG-04 | FR1.6 | Patient Profile | Caregiver does NOT see the accessibility settings banner on patient profile | 1. View a linked patient's profile 2. Check for accessibility banner | No accessibility banner/toggle shown; profile is read-only for caregiver | Medium | PENDING
EMERGENCY NOTIFICATIONS
CG-05 | FR4.6 | Notifications | Caregiver receives push notification when linked patient triggers SOS | 1. Link Caregiver to patient 2. Trigger SOS from patient account 3. Check Caregiver device | Push notification arrives within 5 seconds; notification shows patient name and emergency type | Critical | PENDING
CG-06 | FR3.3 | Notifications | Caregiver receives vibration alert if Vibration Feedback is enabled | 1. Enable Vibration Feedback in Accessibility Settings 2. Trigger SOS from linked patient | Device vibrates on SOS alert in addition to push notification | High | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
CG-07 | FR7.2 | Linking | Patient and caregiver link through an email invitation (many-to-many) | 1. Caregiver invites patient A and patient B 2. Both accept 3. Patient A also links a second caregiver | Caregiver sees both patients; patient A sees both caregivers | High | PENDING
CG-08 | FR6.3, FR6.2 | Live Map | Caregiver sees the live map when a linked patient's SOS is accepted | 1. Linked patient sends SOS 2. Responder accepts and moves 3. Caregiver taps "Track live" | Map shows patient pin, moving ambulance marker, ETA and status timeline | Critical | PENDING
CG-09 | FR4.6 | Notifications | Caregiver receives assigned / arrived / safe updates without duplicate SOS alerts | 1. Run a full SOS to resolution | Exactly one SOS alert, then "responder assigned", "help has arrived" and "patient safe" updates | High | PENDING
CG-10 | Beyond SRS | History | Caregiver emergency history shows real data | 1. Open History after an emergency | Past emergencies of linked patients with status, responder and time; no placeholder names | Medium | PENDING

## MEDICAL
MediFind — MEDICAL Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
MEDICAL PROFILE
MED-01 | FR2.1, FR2.2 | Profile | Patient creates and edits the medical profile | 1. Medical ID → Edit 2. Set blood group, allergies, chronic diseases, medications, disability type 3. Save and reopen | All fields saved and shown on Medical ID; DEAF disability reflected in app mode | Critical | PENDING
MED-02 | FR2.1 | Profile | Saving the medical profile keeps emergency contacts and quick phrases | 1. Add 2 emergency contacts and a quick phrase 2. Edit and save the medical profile | Contacts and quick phrases are unchanged | High | PENDING
MED-03 | FR2.1 | Contacts | Patient adds, calls and deletes emergency contacts | 1. Add contact 2. Tap Call 3. Delete with confirmation | Contact saved; dialer opens; contact removed after confirmation; duplicate phone rejected | Medium | PENDING
MED-04 | FR2.2 | Profile | Sensitive medical fields are encrypted at rest | Inspect MedicalProfile.allergies in the database | Stored value is ciphertext; app and assigned responder see readable values | High | PENDING
MEDICAL REPORTS
MED-05 | FR2.3 | Reports | Upload a report from camera, gallery (image) and PDF | 1. Reports → Upload → Camera 2. Upload from gallery 3. Upload a PDF (≤10 MB) | All three appear in the list with name, type and size | Critical | PENDING
MED-06 | FR2.3 | Reports | Unsupported or oversized files are rejected with a clear message | Upload an .exe and an 11 MB file | Upload refused with an error; nothing added to the list | Medium | PENDING
MED-07 | FR2.4 | Reports | View, rename and delete a report | 1. Open a report 2. Rename it 3. Delete with confirmation | Report opens; new name shown; report removed after confirmation | High | PENDING
DATA SHARING & ISOLATION
MED-08 | FR2.5 | SOS | Assigned responder receives the patient medical summary on accept | 1. Patient with allergies sends SOS 2. Responder accepts | Responder sees blood group, allergies, chronic diseases, medications and DEAF flag | Critical | PENDING
MED-09 | FR2.6 | Isolation | Report files are visible only to the patient, linked caregivers, the active responder and admins | 1. Open a report URL as an unrelated patient 2. As a responder after the emergency is resolved | HTTP 403 in both cases | Critical | PENDING

## CHAT
MediFind — CHAT Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
REAL-TIME MESSAGING
CHT-01 | FR7.1 | Chat | Patient and Responder can exchange real-time text messages during emergency | 1. Active emergency in progress 2. Open chat from both sides 3. Send messages | Messages appear instantly on both sides without page refresh | High | PENDING
CHT-02 | FR7.1 | Chat | Normal patient sees mic button for voice recording in chat | 1. Log in as Normal Patient 2. Open chat screen 3. Inspect input area | Mic icon shown in send button area; tapping it starts voice recording | High | PENDING
CHT-03 | FR3.1, FR3.4 | Chat | Deaf patient does NOT see mic button; send button always shown instead | 1. Log in as Deaf Patient 2. Open chat screen 3. Inspect input area with empty text field | Mic icon NOT shown; send icon shown (slightly dimmed if field empty); no voice recording option | Critical | PENDING
CHT-04 | FR3.4 | Chat | Deaf patient sees Quick Phrases toolbar for one-tap message sending | 1. Log in as Deaf Patient 2. Open chat 3. Look for Quick Phrases bar | Horizontal scrollable quick-phrase chips shown above input; tapping one fills and sends instantly | Critical | PENDING
QUICK PHRASES (DEAF PATIENTS)
CHT-05 | FR3.4 | Quick Phrases | Deaf patient can manage (add/edit/delete) Quick Phrases from Accessibility Settings | 1. Log in as Deaf Patient 2. Go to Accessibility Settings 3. Tap "Manage Quick Phrases" 4. Add a new phrase | Predefined Messages screen opens; new phrase saved and appears in chat toolbar | High | PENDING
CHT-06 | FR3.1 | Quick Phrases | Quick Phrases management option NOT shown for Normal Patient or Responder | 1. Log in as Normal Patient 2. Go to Accessibility Settings 3. Check for Quick Phrases option | "Manage Quick Phrases" option is absent from the screen | High | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
CHT-07 | FR3.4 | Emergency Chat | Patient and assigned responder chat during an emergency | 1. Responder accepts 2. Patient opens Chat from tracking | Messages delivered instantly both ways; deaf patient receives a system briefing message for the responder | High | PENDING
CHT-08 | FR7.2 | Rooms | One caregiver chats separately with multiple patients | 1. Caregiver linked to patients A and B 2. Chat with both | Two independent rooms in chat list | Medium | PENDING
CHT-09 | FR7.3 | Privacy | Messages in one room are never visible to non-members | 1. User C (not a member) requests GET /api/chat/messages/:roomId and joins the socket room | HTTP 403; socket join refused; no messages received | Critical | PENDING
CHT-10 | FR7.4, FR3.3 | Notifications | New message notification with haptic feedback | 1. App in background or on another screen 2. Receive a message | Notification shown and device vibrates (if enabled) | High | PENDING
CHT-11 | FR7.5 | History | Chat history persists across app restarts | 1. Exchange messages 2. Force close and reopen app | Previous messages load in order | High | PENDING
CHT-12 | Beyond SRS | Media | Send image, document, voice note and current location | 1. Use the attachment sheet for each type | Each message delivered and opens correctly; failed send keeps typed text | Medium | PENDING

## PRIVACY_CALLS
MediFind — PRIVACY_CALLS Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
CONTACT DETAILS PRIVACY
PRV-01 | FR7.3 | Privacy | Phone number and email are hidden from users without a care or emergency relationship | GET /api/users/:id as (a) an unrelated patient (b) a responder with no emergency for that patient | phoneNumber and email are empty in both cases | Critical | PASS | 2026-09-17: privacy_e2e — unrelated patient / responder without emergency get empty phone
PRV-02 | FR7.3 | Privacy | Patient and linked caregiver can see each other's phone number | GET /api/users/:id between an accepted caregiver link | Phone number returned both ways | High | PASS | 2026-09-17: privacy_e2e — linked caregiver and patient see each other's phone
PRV-03 | FR5.3 | Privacy | A dispatched responder who has not accepted sees the medical summary but not the patient's contact details | 1. Patient sends SOS 2. Before accepting, responder opens the emergency and the request list | Medical summary visible; patient phone and email absent | Critical | PASS | 2026-09-17: privacy_e2e — dispatched responder reads emergency + medical summary, no phone/email (details and pending list)
PRV-04 | FR5.3 | Privacy | During an open emergency the patient, caregiver and assigned responder can reach each other | 1. Responder accepts 2. Each party reads the other's profile | Phone numbers returned while the emergency is open | High | PASS | 2026-09-17: privacy_e2e — assigned responder, patient and caregiver see phones while the emergency is open
PRV-05 | Beyond SRS | Privacy | When the responder's job is done, contact details are hidden again | 1. Responder resolves 2. Patient, caregiver and responder read each other's profile and history | No phone numbers; history shows the responder name only | Critical | PASS | 2026-09-17: privacy_e2e — after resolve all three lose the phone; history keeps responder name only
PRV-06 | Beyond SRS | Privacy | Responder history and the nearby-responder list never expose contact details | GET /api/responders/history and /api/responders/nearby as a responder | No patient or responder phone/email in the responses | High | PASS | 2026-09-17: privacy_e2e — responder history and nearby-responder list contain no phone/email
PRV-07 | FR5.1 | Dispatch | When one responder accepts, other dispatched requests are closed as taken by another responder | 1. SOS dispatched to 2 responders 2. One accepts 3. Patient opens emergency chat | Other request REJECTED (ASSIGNED_TO_ANOTHER_RESPONDER); chat room is with the accepting responder only | Critical | PASS | 2026-09-17: BUG FIXED — losing requests were COMPLETED and a chat room was created with a responder who never accepted; now REJECTED (taken by another), 19 old rows migrated, room created with accepting responder
EMERGENCY CHAT LOCK
LCK-01 | FR7.3 | Chat | Patient and assigned responder can chat while the emergency is open | Send a message from each side | Both messages delivered (HTTP 201) | High | PASS | 2026-09-17: privacy_e2e — patient and responder messages 201 while open
LCK-02 | Beyond SRS | Chat | After the emergency ends the chat is read-only for both sides | 1. Resolve the emergency 2. Send a message from patient and responder 3. Reopen the room | HTTP 403 CHAT_CLOSED; room isLocked; old messages still readable | Critical | PASS | 2026-09-17: privacy_e2e — after resolve both get 403 CHAT_CLOSED; room isLocked=true; history readable
LCK-03 | Beyond SRS | Chat | App shows the closed state in an ended emergency chat | Open the chat of a resolved emergency in the app | Lock notice instead of the message box; no call button | High | PASS | 2026-09-17: emulator — ended emergency chat shows lock notice, no composer, no call icon
PHONE CALLS (DIALER)
PHN-01 | Beyond SRS | Calls | Hearing patient calls the assigned responder from the tracking screen (use case UC4) | Tap Call on the tracking screen | Phone dialer opens with the responder's number | High | PASS | 2026-09-17: emulator — dialer opened with responder number +923001110003
PHN-02 | Beyond SRS | Calls | Responder calls a hearing patient from the active emergency (use case UC7) | Tap Call patient | Phone dialer opens with the patient's number | High | PASS | 2026-09-17: emulator — dialer opened with patient number +923001110001 (button was missing before)
PHN-03 | Beyond SRS | Calls | Call button in the chat header for patient ↔ caregiver and open emergency chats | Open the chat and tap the call icon | Phone dialer opens with the other person's number | Medium | PASS | 2026-09-17: emulator — chat header call opened +923001110004 (caregiver)
PHN-04 | FR3.1 | Accessibility | No voice-call options are offered in a Deaf patient's chats | Open a chat as / with a Deaf patient | No phone call icon; chat remains the channel | High | PASS | 2026-09-17: emulator — Deaf patient chat header has no call icon
IN-APP VOICE / VIDEO CALLS (WebRTC)
CALL-01 | Beyond SRS | Signalling | Patient calls a linked caregiver in the app | 1. Patient starts a voice call 2. Caregiver accepts 3. Offer/answer exchanged 4. Patient hangs up | Incoming call with caller name; call connects; hang-up reaches the other side | Critical | PASS | 2026-09-17: call_signal_e2e — invite, incoming with caller name, accept, offer/answer relayed, hang-up
CALL-02 | Beyond SRS | Security | Only the two participants exchange call signals; busy users cannot be called | 1. A third user sends a signal for the call 2. Someone calls a user who is on a call | Signal ignored; second caller gets BUSY | High | PASS | 2026-09-17: call_signal_e2e — outsider signal not relayed; BUSY while on another call
CALL-03 | FR3.1 | Accessibility | Calls with a Deaf patient are video only | Start a voice call from and to a Deaf patient, then a video call | Voice refused (VIDEO_ONLY); video call allowed | High | PASS | 2026-09-17: call_signal_e2e — voice call from/to Deaf patient refused (VIDEO_ONLY); video allowed
CALL-04 | Beyond SRS | Signalling | Decline and cancel | 1. Callee declines 2. Caller cancels while ringing | Other side is told immediately and the call screen closes | Medium | PASS | 2026-09-17: call_signal_e2e — decline and cancel reach the other side
CALL-05 | Beyond SRS | Signalling | Unanswered call stops ringing after 45 seconds | Call and do not answer | Both sides get "missed"; call can be retried | Medium | PASS | 2026-09-17: emulator — incoming voice call rang 45 s unanswered, screen closed; caller got call:missed
CALL-06 | Beyond SRS | Security | Responder calls are tied to the open emergency | 1. Patient calls responder during the emergency 2. Responder resolves 3. Patient calls again | Call ends for both when resolved; new call refused | Critical | PASS | 2026-09-17: call_signal_e2e — responder callable only during the emergency; resolve ends the call for both (EMERGENCY_ENDED); emulator: connected voice call closed on resolve
CALL-07 | Beyond SRS | Audit | Call start/end/decline/miss are recorded in the audit log | Make and end a call; check AuditLog entity=Call | Rows with caller, callee, media, duration | Medium | PASS | 2026-09-17: call_signal_e2e — call events written to AuditLog
CALL-08 | Beyond SRS | App | Voice call connects with audio both ways | Two devices: patient calls caregiver and both speak | Both hear each other; mute and speaker work; timer runs | Critical | PASS | 2026-09-17: emulator ↔ browser peer — voice call accepted, timer running, audio bytes flowing both ways. Fixed: offer arriving while the camera started was dropped (now queued), stuck on "Connecting…" (now polls ICE state)
CALL-09 | Beyond SRS | App | Video call shows the remote video and local preview | Start a video call; toggle camera, switch camera, mute | Remote video full screen, own preview small; controls work | High | PASS | 2026-09-17: emulator ↔ browser peer — video call, remote video decoded (158 frames) and local preview shown. Fixed: emulator crash on video (run emulator without Vulkan)
CALL-10 | Beyond SRS | App | Incoming call reaches a phone with the app in the background | Put the callee app in background; call it | Notification appears; tapping opens the ringing call screen | High | PASS | 2026-09-17: app in background — "Incoming video call / Sara Malik is calling you" notification; tapping it opens the Accept/Decline screen
CALL-11 | FR3.1 | Accessibility | Deaf patient sees only video call buttons and a visual incoming-call alert | Deaf patient receives a video call | Flashing screen and vibration; accept/decline buttons | High | PASS | 2026-09-17: Deaf patient — chat header and tracking show only Video call; voice call refused (VIDEO_ONLY); incoming video connects with remote video
PERFORMANCE & AI
PERF-01 | FR8.4 | Performance | SOS countdown opens immediately after Send SOS | Send SOS with location already known | Countdown visible within 1 s (location refined during the countdown) | High | PASS | 2026-09-17: emulator recording — countdown visible ~0.1 s after Send SOS (was 8–10 s waiting for GPS)
PERF-02 | FR8.4 | Performance | Responder reaches navigation right after accepting | Accept an emergency | Active emergency screen within ~1 s | High | PASS | 2026-09-17: responder reaches navigation ~1 s after Accept (was ~15 s)
PERF-03 | FR6.2 | Tracking | Responder marker moves smoothly along the road | Watch the tracking map during a drive | No backward jumps or U-turn loops; heading follows the road | Medium | PASS | 2026-09-17: frame analysis — no backward jumps or U-turn loops; remaining ~0.3 s marker blink about every 16 s on the emulator (route redraw)
AI-01 | Beyond SRS | AI | AI symptom check suggests the emergency type | Type symptoms on the emergency type screen and tap Suggest | Suggested type with confidence and reason; type preselected | Medium | PASS | 2026-09-17: Gemini free tier (gemini-3.1-flash-lite) — "chest pain spreading to left arm" → Cardiac 98%, ~2 s
AI-02 | Beyond SRS | AI | AI quick replies are personalised for a Deaf patient | Deaf patient opens Quick messages during an emergency | Suggestions reflect the medical profile | Medium | PASS | 2026-09-17: quick replies personalised from medical profile (asthma, Salbutamol, Penicillin allergy)
LAYOUT & ORIENTATION
UX-01 | NFR | Usability | App stays in portrait when the phone is rotated | Open the responder dashboard and rotate the phone | Screen stays portrait; nothing squeezed or cut off | High | PASS | 2026-09-18: responder app on emulator rotated to landscape stays portrait (before: dashboard squeezed into a strip)
UX-02 | NFR | Usability | On a tablet or wide screen the app is centred, not stretched or stuck to one side | Open the app on a tablet (or web/desktop) | App shown as a centred column with even margins | Medium | PASS | 2026-09-18: emulator resized to 1600x2560 tablet, portrait and landscape: centred 600dp column, no stretched or one-sided layout

## PROFILE
MediFind — PROFILE Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
OWN PROFILE
PRF-01 | Beyond SRS | Profile | Any user can view and edit their own profile (name, phone, avatar) | 1. Log in 2. Go to Profile 3. Tap Edit 4. Change name 5. Save | Profile updated; new name reflected on screen and in subsequent API calls | High | PENDING
PRF-02 | Beyond SRS | Profile | User can upload a profile avatar image | 1. Go to Profile 2. Tap avatar 3. Select image from gallery 4. Save | Avatar uploaded; new image shown on profile screen | Medium | PENDING
ACCOUNT DELETION
PRF-03 | Beyond SRS | Account Deletion | User can delete account; redirected to Login with no black screen | 1. Log in 2. Go to Profile Settings 3. Tap Delete Account 4. Confirm | Account deleted; smooth navigation to Login screen; NO black overlay flash during transition | Critical | PENDING
PRF-04 | Beyond SRS | Account Deletion | Confirmation dialog is shown before account deletion; cancelling keeps the account | 1. Profile → Delete account 2. Tap Cancel in the confirmation dialog | Account is NOT deleted; user stays on Profile screen | High | PENDING
PRF-05 | Beyond SRS | Account Deletion | After deletion, user cannot log back in with deleted credentials | 1. Delete account 2. Try to log in with old credentials | Error "Invalid email or password"; access denied | High | PENDING

## ACCESSIBILITY
MediFind — ACCESSIBILITY Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
NORMAL PATIENT — ACCESSIBILITY
ACC-01 | FR3.1 | Accessibility | Normal patient sees Voice Guidance toggle; Deaf patient does NOT | 1. Log in as Normal Patient → open Accessibility Settings 2. Log in as Deaf Patient → open Accessibility Settings | Normal Patient: Voice Guidance toggle visible Deaf Patient: Toggle absent | High | PENDING
ACC-02 | FR3.1 | Accessibility | Text-Only Interface toggle shown ONLY for Deaf patient | 1. Log in as Normal Patient → Accessibility Settings 2. Log in as Deaf Patient → Accessibility Settings | Normal Patient: toggle absent Deaf Patient: toggle present and functional | High | PENDING
DEAF PATIENT — ACCESSIBILITY
ACC-03 | FR3.4 | Accessibility | Deaf patient sees "Communication" section with Manage Quick Phrases shortcut | 1. Log in as Deaf Patient 2. Open Accessibility Settings 3. Scroll to Communication section | "Manage Quick Phrases" card visible; tapping navigates to /predefined-messages | High | PENDING
ACC-04 | FR3.1 | Accessibility | Deaf patient tip card shows "Deaf Mode Tips" with vibration advice | 1. Log in as Deaf Patient 2. Open Accessibility Settings 3. Scroll to tip card | Tip card title: "Deaf Mode Tips"; content mentions vibration and visual alerts | Medium | PENDING
RESPONDER — ACCESSIBILITY
ACC-05 | FR5.2 | Accessibility | Responder sees "Voice Alerts" section with Hands-Free Voice Alerts toggle | 1. Log in as Responder 2. Open Accessibility Settings | "Voice Alerts" section visible; toggle labelled "Hands-Free Voice Alerts" | High | PENDING
ACC-06 | Beyond SRS | Accessibility | Responder tip card shows "Response Guidelines" | 1. Log in as Responder 2. Open Accessibility Settings 3. Scroll to tip card | Tip title: "Response Guidelines"; content advises on voice alerts and vibration | High | PENDING
CAREGIVER — ACCESSIBILITY
ACC-07 | Beyond SRS | Accessibility | Caregiver sees "Monitoring Tips" card; no Voice Guidance section | 1. Log in as Caregiver 2. Open Accessibility Settings | Tip card: "Monitoring Tips"; no Voice Guidance / Audio section shown | Medium | PENDING
UNIVERSAL ACCESSIBILITY
ACC-08 | FR3.2 | Accessibility | Font size slider ranges 100%–150% and scales text app-wide without clipping | 1. Accessibility → Font size 2. Move to 100% then 150% 3. Visit Home, SOS, Chat, Profile | Cannot go below 100%; at 150% all screens scale text with no clipped or overlapping labels | Medium | PENDING
ACC-09 | FR3.2 | Accessibility | High Contrast Mode toggle available to all roles | 1. Log in as any role 2. Enable High Contrast Mode | UI colour scheme changes to high-contrast palette immediately | Medium | PENDING
ACC-10 | FR3.5 | Accessibility | Large Buttons Mode toggle available to all roles | 1. Enable Large Buttons Mode 2. Navigate through the app | Tap targets visibly larger across all interactive elements | Medium | PENDING
ACC-11 | Beyond SRS | Accessibility | "Reset to Profile Defaults" restores role-appropriate defaults | 1. Change multiple settings 2. Tap "Reset to Profile Defaults" | Settings restored to role-appropriate defaults; SnackBar confirms reset | Low | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
ACC-12 | FR3.1 | Deaf Mode | Deaf patient gets a full-screen visual alert when help is assigned and arrives | 1. Deaf patient sends SOS 2. Responder accepts, then arrives | Full-screen high-contrast alert with flashing border and vibration on every screen; no audio | Critical | PENDING
ACC-13 | FR3.4 | Deaf Mode | Deaf patient can show a communication card to bystanders | 1. Home → Show to people nearby | Full-screen card: "I am deaf, please write or type", name, blood group, allergies, Call 1122 | High | PENDING
ACC-14 | FR3.2 | Display | Accessibility settings are saved per user account | 1. Deaf patient enables settings 2. Log out, log in as another user | Second user sees their own defaults, not the deaf patient's settings | Medium | PENDING

## NOTIFICATIONS
MediFind — NOTIFICATIONS Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
INDIVIDUAL NOTIFICATIONS (Admin Web Portal)
NTF-01 | Beyond SRS | Notifications | Admin can send individual notification by entering a target email address | 1. Log in as Admin 2. Go to System Notifications 3. Select "Individual" 4. Enter valid email 5. Fill title/body 6. Send | Notification delivered only to the specified user; no other users receive it | Critical | PENDING
NTF-02 | Beyond SRS | Notifications | Form blocks submission if Individual is selected but target email is empty | 1. Select recipient type = Individual 2. Leave email field blank 3. Click Send | Error shown: "Please enter the target email address for individual notification"; form NOT submitted | Critical | PENDING
NTF-03 | Beyond SRS | Notifications | Individual notification does NOT broadcast to all users | 1. Send individual notification to user A 2. Check user B and user C accounts | Only user A receives the notification; users B and C receive nothing | Critical | PENDING
BROADCAST NOTIFICATIONS
NTF-04 | Beyond SRS | Notifications | Admin can broadcast to ALL users | 1. Select recipient type = All 2. Fill title/body 3. Send | All registered users receive in-app and/or push notification | High | PENDING
NTF-05 | Beyond SRS | Notifications | Admin can broadcast to a specific role (Patient/Responder/Caregiver) | 1. Select recipient type = Patient 2. Send notification | Only Patient-role accounts receive the notification | High | PENDING
IN-APP NOTIFICATIONS
NTF-06 | FR7.4 | Notifications | In-app notification appears without restart and new chat messages vibrate | 1. Have app open 2. Admin sends individual notification to logged-in user | Bell badge increments and the item appears within 3 s; device vibrates for new messages when vibration is enabled | High | PENDING
NTF-07 | Beyond SRS | Notifications | Notification history logged in admin broadcast history | 1. Send any notification 2. Go to Notification History tab in admin portal | New entry visible with recipient group, title, timestamp, and status | Medium | PENDING
AI DRAFT GENERATION
NTF-08 | Beyond SRS | AI Draft | Admin can use AI to generate notification title and body from a prompt | 1. Enter AI prompt 2. Click Generate Draft | Title and body fields populated with AI-generated content; editable before sending | Low | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
NTF-09 | Beyond SRS | Push Service | Push notifications arrive when the app is closed (self-hosted, no Firebase) | 1. Log in, allow notifications and background activity 2. Close the app 3. Trigger a notification | System notification appears; "MediFind emergency alerts are active" service notification present | Critical | PENDING
NTF-10 | Beyond SRS | Push Service | Notifications missed while offline are delivered after reconnect | 1. Turn off internet 2. Send a notification to the user 3. Reconnect | Notification delivered once after reconnect; admin Comm Audit status changes pending → delivered | High | PENDING
NTF-11 | Beyond SRS | Push Service | Tapping a notification opens the correct screen for the role | 1. Tap SOS (responder), patient emergency (caregiver), chat message | Opens request screen, live tracking, chat room respectively — also from a closed app | High | PENDING
NTF-12 | Beyond SRS | Push Service | Expired emergency alerts are never shown late | 1. Keep device offline > 10 minutes after an SOS alert 2. Reconnect | The stale SOS alert is not shown | Medium | PENDING

## NAVIGATION_UI
MediFind — NAVIGATION_UI Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
NAVIGATION & LAYOUT
NAV-01 | FR8.1 | Drawer | Each role has a unified sidebar (AppDrawer) with role-specific items | Open the menu as patient, caregiver and responder | Drawer opens from the header menu button with the correct items per role | High | PENDING
NAV-02 | FR8.2 | Routing | Switching tabs preserves each tab's state and back navigation works | 1. Scroll a list in tab A 2. Switch to tab B and back 3. Use system back | Scroll position/state kept; back returns to the previous screen without flicker | Medium | PENDING
NAV-03 | FR8.3 | Dashboard | Role dashboards show quick action grids | Open Home as each role | Grid of labelled actions (e.g. Medical ID, Contacts, Caregivers, Messages) navigating correctly | Medium | PENDING
NAV-04 | FR8.4 | Performance | Map and chat screens render smoothly (~60 FPS) | 1. flutter run --profile 2. Enable performance overlay 3. Scroll chat with 100+ messages and watch live tracking for 1 minute | No sustained red frames in the UI/raster graphs | Medium | PENDING
NAV-05 | FR3.5 | Touch targets | Large buttons mode enlarges tap targets across screens | Enable Large buttons, visit Home, SOS, Chat | Primary actions visibly larger (≥ 56 dp) | Medium | PENDING

## ADMIN_PORTAL
MediFind — ADMIN_PORTAL Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
USER MANAGEMENT
ADM-01 | FR9.2 | User Management | Admin can view all registered users with role, status, and join date | 1. Log in as Admin 2. Navigate to User Management | Paginated table showing all users with columns: name, email, role, status, joined date | High | PENDING
ADM-02 | FR9.2 | User Management | Admin can search users by name or email | 1. Enter partial email in search box | Table filters to matching users in real-time | High | PENDING
ADM-03 | FR9.3 | User Management | Admin can deactivate / suspend a user account | 1. Find user 2. Change status to Suspended | User can no longer log in; account status updated in table | Medium | PENDING
RESPONDER VERIFICATION
ADM-04 | FR9.5 | Verification | Admin can approve or reject a pending responder application | 1. Go to Responder Verification 2. View pending applicant 3. Approve | Responder status set to ACTIVE; responder can now receive emergency alerts | Critical | PENDING
ADM-05 | FR9.5 | Verification | Rejected responder receives notification of rejection | 1. Reject a pending responder 2. Check responder email/in-app | Notification sent; responder account marked REJECTED; cannot log into active features | Critical | PENDING
ADM-06 | FR9.4 | Verification | Admin can view uploaded employee card document for verification | 1. Open pending responder application 2. Click on employee card attachment | Document opens/downloads correctly for admin review | High | PENDING
DASHBOARD
ADM-07 | FR9.6 | Dashboard | Dashboard shows live count of active emergencies, total users, and pending verifications | 1. Log in as Admin 2. Open Dashboard | Stats cards display current counts; data refreshes without full page reload | Medium | PENDING
ADM-08 | FR9.1, FR9.7 | Dashboard | Admin dashboard accessible only by ADMIN role accounts | 1. Log in as Patient 2. Attempt to access /admin URL directly | Redirected to login or 403 error; admin pages not accessible | Medium | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
ADM-09 | FR9.2 | Users | Admin filters users by role and status | 1. User Management → Responders tab → Inactive filter | Only matching users listed | High | PENDING
ADM-10 | FR9.3 | Users | Admin deletes a user account (soft delete, audit preserved) | 1. Delete a test user and confirm | User removed from active lists, sessions revoked, cannot log in; payment/audit history kept | High | PENDING
ADM-11 | FR6.1 | SOS Logistics | Admin live map shows active SOS and moving responders | 1. Open SOS Logistics during an active emergency | SOS pin and moving motorbike ambulance marker update live | Medium | PENDING
ADM-12 | Beyond SRS | Subscriptions | Admin changes or cancels a user's subscription plan | 1. Subscriptions → Change plan → confirm | Plan updated after refresh; audit log entry ADMIN_UPDATE_SUBSCRIPTION | Medium | PENDING
ADM-13 | Beyond SRS | Security | Maintenance mode blocks non-admin API usage | 1. Settings → enable Maintenance mode 2. Use the mobile app | App requests return 503 maintenance message; admin portal keeps working | Low | PENDING

## BACKEND_API
MediFind — BACKEND_API Requirements & Test Cases
REQ ID | SRS Ref | Module | Requirement Description | Test Steps | Expected Result | Priority | Status | Notes / Defect Ref
AUTHENTICATION ENDPOINTS
API-01 | FR1.1 | Auth API | POST /api/auth/register — creates user and returns 201 | 1. Send POST with valid body 2. Check response | HTTP 201; user record in DB; verification email queued | Critical | PENDING
API-02 | FR1.2 | Auth API | POST /api/auth/login — returns access and refresh tokens | 1. Send POST with valid credentials | HTTP 200; response data contains token (access JWT), refreshToken, role and fullName | Critical | PENDING
API-03 | FR1.2 | Auth API | POST /api/auth/refresh-token — issues a new access token; refresh tokens cannot call protected APIs | 1. Call refresh-token with a valid refreshToken 2. Call GET /api/users/profile using the refresh token as Bearer | Step 1: HTTP 200 with token/accessToken. Step 2: HTTP 401 | High | PENDING
API-04 | Beyond SRS | Auth API | DELETE /api/users/me — deletes account and returns 200 | 1. Send DELETE with valid auth token | HTTP 200; user record removed; subsequent login attempts return 401 | High | PENDING
EMERGENCY ENDPOINTS
API-05 | FR4.5 | Emergency API | POST /api/emergencies — creates emergency and notifies nearby responders | 1. Send POST with patient coords and emergency type | HTTP 201; emergency ACTIVE; nearby responders receive SOS_TRIGGERED via socket "notification" and self-hosted "push" events | Critical | PENDING
API-06 | FR5.1 | Emergency API | POST /api/responders/emergencies/:id/accept — assigns responder (first accept wins) | 1. Two responders call accept at the same time | Exactly one HTTP 200 (emergency ASSIGNED, EMERGENCY_STATUS_CHANGE emitted); the other gets HTTP 400 | Critical | PASS | 2026-09-17: first accept 200, second accept 400; accept now responds in 72 ms (AI brief moved to background)
API-07 | FR6.2 | Emergency API | PATCH /api/emergencies/:id/status — assigned responder updates EN_ROUTE / ARRIVED | 1. Send PATCH with new status value | HTTP 200 for the assigned responder with EMERGENCY_STATUS_CHANGE emitted; any other responder or patient gets HTTP 403 | High | PENDING
NOTIFICATION ENDPOINTS
API-08 | Beyond SRS | Notifications API | POST /api/notifications/broadcast with recipientType=INDIVIDUAL — delivers to one user only | 1. POST with { recipientType:"INDIVIDUAL", targetId:"user@email.com", title, body } 2. Check all user sockets | HTTP 200; only the target user's socket room (notifications:userId) receives the event | Critical | PENDING
API-09 | Beyond SRS | Notifications API | POST /api/notifications/broadcast with missing targetId for INDIVIDUAL — returns 400 | 1. POST with { recipientType:"INDIVIDUAL", targetId:"" } | HTTP 400; error message "targetId is required for individual messages" | High | PENDING
MIDDLEWARE & SECURITY
API-10 | FR1.6 | Security | Protected endpoints reject requests without valid JWT | 1. Send request to /api/users/me with no Authorization header | HTTP 401 Unauthorized | Critical | PENDING
API-11 | FR1.6, FR9.7 | Security | Role-based endpoints enforce role check (e.g., admin-only routes) | 1. Send request to /api/admin/* as a Patient account | HTTP 403 Forbidden | High | PENDING
API-12 | FR2.3 | Security | File uploads are validated for type and size | 1. Upload an .exe 2. Upload an 11 MB image | Both rejected with HTTP 400 and a clear message; images, PDF, audio and Word files ≤10 MB accepted | Medium | PENDING
ADDED IN v2.0 — SRS GAPS & NEW FEATURES
API-13 | FR6.3 | Emergencies | GET /api/emergencies/history — patient own / caregiver linked patients | Call as patient, caregiver and responder | Patient and caregiver: HTTP 200 with emergencies and assigned responder; responder: HTTP 403 | Medium | PENDING
API-14 | Beyond SRS | Push | GET /api/notifications/pending and POST /api/notifications/ack | 1. Queue a push for an offline user 2. GET pending 3. POST ack with ids 4. GET pending | Step 2 lists the message; after ack step 4 returns an empty list | High | PENDING
API-15 | FR2.6 | Security | GET /api/emergencies/:id enforces access control | Request another patient's emergency as a patient | HTTP 403 | Critical | PENDING
API-16 | FR6.1 | Socket | Socket.io connections require a valid JWT | Connect without a token, then with a valid token | Without token: connection rejected "Unauthorized"; with token: user auto-joins own notification room | Critical | PENDING

## CHANGE_LOG
MediFind — Changes from Version 1.0 (2026-05-30) to 2.2
Test ID | Type | Change | Reason
AUTH-01 | Updated | Description / steps / expected result corrected | Patients provide a CNIC number; only responders upload document photos. Verification is by email OTP.
AUTH-03 | Updated | Description / steps / expected result corrected | Responder application requires CNIC front/back, employee card, driving licence and motorbike documents.
AUTH-04 | Updated | Description / steps / expected result corrected | Caregiver–patient linking is done after login by email invitation (supports many-to-many, FR7.2).
AUTH-05 | Updated | Description / steps / expected result corrected | Matches the actual server message.
AUTH-08 | Updated | Description / steps / expected result corrected | Matches the actual server message and lockout warning.
AUTH-09 | Updated | Description / steps / expected result corrected | Matches the actual server message.
SOS-01 | Updated | Description / steps / expected result corrected | Aligned with SRS FR4.1/FR4.3: press-and-hold plus a pre-send countdown (false SOS prevention). The SRS 10 s window was extended to 60 s by project decision; Send SOS now skips the wait.
SOS-03 | Updated | Description / steps / expected result corrected | Countdown cancellation must not create any server record (SRS FR4.3).
SOS-04 | Updated | Description / steps / expected result corrected | The app must never send a default/fake location.
SOS-06 | Updated | Description / steps / expected result corrected | Timeline includes Resolved.
RSP-01 | Updated | Description / steps / expected result corrected | Dispatch radius is 10 km and push arrives with the app closed (self-hosted push).
RSP-02 | Updated | Description / steps / expected result corrected | Alert card content as implemented.
RSP-05 | Updated | Description / steps / expected result corrected | SRS FR5.3 requires medical info and the DEAF flag.
RSP-07 | Updated | Description / steps / expected result corrected | All nearby responders are alerted at once; unaccepted SOS is re-dispatched after 60 s with admin escalation.
RSP-09 | Updated | Description / steps / expected result corrected | Arrival and resolution are separate steps; resolution records an outcome.
PRF-04 | Updated | Description / steps / expected result corrected | Requirement and expected result described different actions.
ACC-08 | Updated | Description / steps / expected result corrected | SRS FR3.2 requires scaling up to 150%.
NTF-06 | Updated | Description / steps / expected result corrected | SRS FR7.4 requires haptic alerts for messages.
API-02 | Updated | Description / steps / expected result corrected | Login returns token + refreshToken.
API-03 | Updated | Description / steps / expected result corrected | Real path is /api/auth/refresh-token; security check added.
API-05 | Updated | Description / steps / expected result corrected | Responders are notified with SOS_TRIGGERED notification and push events, not NEW_EMERGENCY.
API-06 | Updated | Description / steps / expected result corrected | Real endpoint is POST /api/responders/emergencies/:id/accept; concurrency added (FR5.1).
API-07 | Updated | Description / steps / expected result corrected | Only the assigned responder may update status.
API-12 | Updated | Description / steps / expected result corrected | Covers registration, report and chat uploads.
AUTH-13 | Added | Account locks for 30 minutes after 5 failed login attempts | SRS gap FR1.2
AUTH-14 | Added | User resets a forgotten password with an emailed 6-digit OTP | SRS gap FR1.5
AUTH-15 | Added | Reset/verification code is invalidated after 5 wrong attempts | SRS gap FR1.5
AUTH-16 | Added | Public registration cannot create an ADMIN account | SRS gap FR1.4, FR1.6
AUTH-17 | Added | Deactivated account cannot log in and existing sessions stop working | SRS gap FR9.3
SOS-10 | Added | Patient selects a medical emergency category | SRS gap FR4.4
SOS-11 | Added | Patient sees responder ETA that updates while the responder moves | SRS gap FR6.2
SOS-12 | Added | A quick accidental tap on SOS does not start an emergency | SRS gap FR4.1
SOS-13 | Added | A second SOS while one is open returns the existing emergency (no duplicate dispatch) | SRS gap FR4.5
SOS-14 | Added | After sending, the patient can still cancel within the server cancellation window | SRS gap FR4.3
SOS-15 | Added | Offline patient can still call or SMS Rescue 1122 | New feature (beyond SRS)
SOS-16 | Added | Patient rates the responder after resolution (once) | New feature (beyond SRS)
RSP-10 | Added | Responder resolves the emergency with an outcome | SRS gap FR6.2
RSP-11 | Added | Only one of two simultaneous accepts succeeds | SRS gap FR5.1
RSP-12 | Added | Offline responders are not dispatched | SRS gap FR5.4
RSP-13 | Added | Navigate opens turn-by-turn directions to the patient | SRS gap FR6.4
RSP-14 | Added | Responder location is shared live every few seconds during an active emergency | SRS gap FR6.1
RSP-15 | Added | Responder cancelling an accepted job re-dispatches the SOS | New feature (beyond SRS)
CG-07 | Added | Patient and caregiver link through an email invitation (many-to-many) | SRS gap FR7.2
CG-08 | Added | Caregiver sees the live map when a linked patient's SOS is accepted | SRS gap FR6.3, FR6.2
CG-09 | Added | Caregiver receives assigned / arrived / safe updates without duplicate SOS alerts | SRS gap FR4.6
CG-10 | Added | Caregiver emergency history shows real data | New feature (beyond SRS)
CHT-07 | Added | Patient and assigned responder chat during an emergency | SRS gap FR3.4
CHT-08 | Added | One caregiver chats separately with multiple patients | SRS gap FR7.2
CHT-09 | Added | Messages in one room are never visible to non-members | SRS gap FR7.3
CHT-10 | Added | New message notification with haptic feedback | SRS gap FR7.4, FR3.3
CHT-11 | Added | Chat history persists across app restarts | SRS gap FR7.5
CHT-12 | Added | Send image, document, voice note and current location | New feature (beyond SRS)
ACC-12 | Added | Deaf patient gets a full-screen visual alert when help is assigned and arrives | SRS gap FR3.1
ACC-13 | Added | Deaf patient can show a communication card to bystanders | SRS gap FR3.4
ACC-14 | Added | Accessibility settings are saved per user account | SRS gap FR3.2
NTF-09 | Added | Push notifications arrive when the app is closed (self-hosted, no Firebase) | New feature (beyond SRS)
NTF-10 | Added | Notifications missed while offline are delivered after reconnect | New feature (beyond SRS)
NTF-11 | Added | Tapping a notification opens the correct screen for the role | New feature (beyond SRS)
NTF-12 | Added | Expired emergency alerts are never shown late | New feature (beyond SRS)
ADM-09 | Added | Admin filters users by role and status | SRS gap FR9.2
ADM-10 | Added | Admin deletes a user account (soft delete, audit preserved) | SRS gap FR9.3
ADM-11 | Added | Admin live map shows active SOS and moving responders | SRS gap FR6.1
ADM-12 | Added | Admin changes or cancels a user's subscription plan | New feature (beyond SRS)
ADM-13 | Added | Maintenance mode blocks non-admin API usage | New feature (beyond SRS)
API-13 | Added | GET /api/emergencies/history — patient own / caregiver linked patients | SRS gap FR6.3
API-14 | Added | GET /api/notifications/pending and POST /api/notifications/ack | New feature (beyond SRS)
API-15 | Added | GET /api/emergencies/:id enforces access control | SRS gap FR2.6
API-16 | Added | Socket.io connections require a valid JWT | SRS gap FR6.1
PRV-01 | Added | Phone number and email are hidden from users without a care or emergency relationship | New sheet PRIVACY_CALLS; SRS FR7.3
PRV-02 | Added | Patient and linked caregiver can see each other's phone number | New sheet PRIVACY_CALLS; SRS FR7.3
PRV-03 | Added | A dispatched responder who has not accepted sees the medical summary but not the patient's contact details | New sheet PRIVACY_CALLS; SRS FR5.3
PRV-04 | Added | During an open emergency the patient, caregiver and assigned responder can reach each other | New sheet PRIVACY_CALLS; SRS FR5.3
PRV-05 | Added | When the responder's job is done, contact details are hidden again | New sheet PRIVACY_CALLS; beyond SRS
PRV-06 | Added | Responder history and the nearby-responder list never expose contact details | New sheet PRIVACY_CALLS; beyond SRS
PRV-07 | Added | When one responder accepts, other dispatched requests are closed as taken by another responder | New sheet PRIVACY_CALLS; SRS FR5.1
LCK-01 | Added | Patient and assigned responder can chat while the emergency is open | New sheet PRIVACY_CALLS; SRS FR7.3
LCK-02 | Added | After the emergency ends the chat is read-only for both sides | New sheet PRIVACY_CALLS; beyond SRS
LCK-03 | Added | App shows the closed state in an ended emergency chat | New sheet PRIVACY_CALLS; beyond SRS
PHN-01 | Added | Hearing patient calls the assigned responder from the tracking screen (use case UC4) | New sheet PRIVACY_CALLS; beyond SRS
PHN-02 | Added | Responder calls a hearing patient from the active emergency (use case UC7) | New sheet PRIVACY_CALLS; beyond SRS
PHN-03 | Added | Call button in the chat header for patient ↔ caregiver and open emergency chats | New sheet PRIVACY_CALLS; beyond SRS
PHN-04 | Added | No voice-call options are offered in a Deaf patient's chats | New sheet PRIVACY_CALLS; SRS FR3.1
CALL-01 | Added | Patient calls a linked caregiver in the app | New sheet PRIVACY_CALLS; beyond SRS
CALL-02 | Added | Only the two participants exchange call signals; busy users cannot be called | New sheet PRIVACY_CALLS; beyond SRS
CALL-03 | Added | Calls with a Deaf patient are video only | New sheet PRIVACY_CALLS; SRS FR3.1
CALL-04 | Added | Decline and cancel | New sheet PRIVACY_CALLS; beyond SRS
CALL-05 | Added | Unanswered call stops ringing after 45 seconds | New sheet PRIVACY_CALLS; beyond SRS
CALL-06 | Added | Responder calls are tied to the open emergency | New sheet PRIVACY_CALLS; beyond SRS
CALL-07 | Added | Call start/end/decline/miss are recorded in the audit log | New sheet PRIVACY_CALLS; beyond SRS
CALL-08 | Added | Voice call connects with audio both ways | New sheet PRIVACY_CALLS; beyond SRS
CALL-09 | Added | Video call shows the remote video and local preview | New sheet PRIVACY_CALLS; beyond SRS
CALL-10 | Added | Incoming call reaches a phone with the app in the background | New sheet PRIVACY_CALLS; beyond SRS
CALL-11 | Added | Deaf patient sees only video call buttons and a visual incoming-call alert | New sheet PRIVACY_CALLS; SRS FR3.1
PERF-01 | Added | SOS countdown opens immediately after Send SOS | New sheet PRIVACY_CALLS; SRS FR8.4
PERF-02 | Added | Responder reaches navigation right after accepting | New sheet PRIVACY_CALLS; SRS FR8.4
PERF-03 | Added | Responder marker moves smoothly along the road | New sheet PRIVACY_CALLS; SRS FR6.2
AI-01 | Added | AI symptom check suggests the emergency type | New sheet PRIVACY_CALLS; beyond SRS
AI-02 | Added | AI quick replies are personalised for a Deaf patient | New sheet PRIVACY_CALLS; beyond SRS
UX-01 | Added | App stays in portrait when the phone is rotated | New sheet PRIVACY_CALLS; SRS NFR
UX-02 | Added | On a tablet or wide screen the app is centred, not stretched or stuck to one side | New sheet PRIVACY_CALLS; SRS NFR
MED-01 | Added | Patient creates and edits the medical profile | New sheet MEDICAL; SRS FR2.1, FR2.2
MED-02 | Added | Saving the medical profile keeps emergency contacts and quick phrases | New sheet MEDICAL; SRS FR2.1
MED-03 | Added | Patient adds, calls and deletes emergency contacts | New sheet MEDICAL; SRS FR2.1
MED-04 | Added | Sensitive medical fields are encrypted at rest | New sheet MEDICAL; SRS FR2.2
MED-05 | Added | Upload a report from camera, gallery (image) and PDF | New sheet MEDICAL; SRS FR2.3
MED-06 | Added | Unsupported or oversized files are rejected with a clear message | New sheet MEDICAL; SRS FR2.3
MED-07 | Added | View, rename and delete a report | New sheet MEDICAL; SRS FR2.4
MED-08 | Added | Assigned responder receives the patient medical summary on accept | New sheet MEDICAL; SRS FR2.5
MED-09 | Added | Report files are visible only to the patient, linked caregivers, the active responder and admins | New sheet MEDICAL; SRS FR2.6
SEC-01 | Added | SOS requires press-and-hold before it starts | New sheet SECURITY_SOS; SRS FR4.1
SEC-02 | Added | Cancelling during the 60-second countdown sends nothing to the server | New sheet SECURITY_SOS; SRS FR4.3
SEC-03 | Added | SOS from a mock (fake) GPS location is refused in production | New sheet SECURITY_SOS; SRS FR4.2
SEC-04 | Added | More than 5 SOS in one hour is refused | New sheet SECURITY_SOS; SRS FR4.5
SEC-05 | Added | SOS outside Pakistan coordinates is refused | New sheet SECURITY_SOS; SRS FR4.2
SEC-06 | Added | Responder must add a note when closing as False alarm or Patient not found | New sheet SECURITY_SOS; SRS FR6.2
SEC-07 | Added | Patient is warned when an SOS is marked as a false alarm | New sheet SECURITY_SOS; beyond SRS
SEC-08 | Added | 3 false alarms in 30 days alerts admins for review | New sheet SECURITY_SOS; beyond SRS
SEC-09 | Added | Patient-cancelled SOS never counts as a false alarm | New sheet SECURITY_SOS; beyond SRS
SEC-10 | Added | Refresh token cannot be used as an access token | New sheet SECURITY_SOS; SRS FR1.6
SEC-11 | Added | Users cannot join emergency or chat rooms they do not belong to | New sheet SECURITY_SOS; SRS FR1.6
SEC-12 | Added | Paid plan upgrade requires a verified Stripe payment | New sheet SECURITY_SOS; beyond SRS
SEC-13 | Added | Only the assigned responder can update or resolve an emergency | New sheet SECURITY_SOS; SRS FR5.1
NAV-01 | Added | Each role has a unified sidebar (AppDrawer) with role-specific items | New sheet NAVIGATION_UI; SRS FR8.1
NAV-02 | Added | Switching tabs preserves each tab's state and back navigation works | New sheet NAVIGATION_UI; SRS FR8.2
NAV-03 | Added | Role dashboards show quick action grids | New sheet NAVIGATION_UI; SRS FR8.3
NAV-04 | Added | Map and chat screens render smoothly (~60 FPS) | New sheet NAVIGATION_UI; SRS FR8.4
NAV-05 | Added | Large buttons mode enlarges tap targets across screens | New sheet NAVIGATION_UI; SRS FR3.5
PRF-01 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
PRF-02 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
PRF-03 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
PRF-05 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
NTF-01 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
NTF-02 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
NTF-03 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
NTF-04 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
NTF-05 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
NTF-07 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
NTF-08 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
ACC-06 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
ACC-07 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
ACC-11 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
AUTH-12 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
API-04 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
API-08 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement
API-09 | Re-classified | Marked "Beyond SRS" in the SRS Ref column | Valid feature test with no matching SRS functional requirement